## Sheet1
ADMIN ACTIVITY USER FLOW – ROLES (pg no. 8,9,10)

ROLES:
In admin activity user flow we have a functionality called as ROLES, which contains the details regarding the user roles.
what is user roles?
user roles is term that describes the different levels of access the user have on the site.
Here admin will be able to view user roles and their discription, admin will also be able to add user role, delete user roles, view application access of the roles and also viewing and assigning admins to the roles.

REQUIREMENT ANALYSIS:
software requirement:-
Vs code – React js
Spring tool suite – spring boot services
Mysql workbench – DataBase
postman

IMPACT ANALYSIS:
Users, roles and permission are the key components of website security, users are the people, roles are their functions, and permission define what authorizations those functions have. Setting these up incorrectly can compromise your website’s security.

Design:

usecase diagram

				Roles

				add user roles
					assign application access

				delete user roles
		admin
					assign admin to role

sequence diagram:

		admin			system

			create user role

			user role created

			assign application access

			application access added successfully

			assign admin to roles

			added admin to role

			delete role

			user role deleted successfully

Review
pair review and lead review

Developing:

-List of activities required to develop functionality using React.js
creating actions such as adding role and deleting role
creating table to display the existing roles
creating action to assign applications to the roles
creating action to assign admins to roles
craeting action to view assigned admins and application access to particular role
using axios api to integrate with spring boot

-List of activities required to develop functionality using spring boot services
creating classes for roles,admin and application as models
creating controller classes for roles,admin and application
creating JPA repository
creating services

-List of activities required to develop functionality using DB schema
create a database
create table for roles, admin, applications

code has to be updated in respective git repository
Then code has to be reviewed : pair review
		: lead review

Testing
unit testing
api testing
performance testing

Deployment
After successfully passing all the test cases , will be released to production.